## Intro
eResearch Collaboration Projects (eRCP) offer a fixed effort approach while varying the scope. This means if a project is awarded a month of developer time we seek to deliver on as many features as possible in that time, but do not typically allow for overrun.
We borrow the http://en.wikipedia.org/wiki/MoSCoW_method method of prioritsation:
MUST: are the requirements for the solution to be considered a success. If ANY must requirement is not met the project is considered a failure (Also a backronym for the Minimum Usable SubseT)
SHOULD: are high-priority requirements to be delivered where possible, but may be satisfied in other ways if strictly necessary.
COULD: requirements are desirable if time permits
WON'T: requirements will not be implemented in the current project but help set ambition / direction for future work
The goal is not to lock a project into a fixed trajectory but to focus it on the essential items and ensure the Minimum Usable Subset is delivered.
When scoping a project we simply create a list where each item is assigned to M/S/C/W and its required effort is estimated in time (days) or difficulty, depending of developer preference. When using time, granularity should probably be no finer than half-days, or the list risks getting too long / overly ambitious. Similar reasoning applies for difficulty rating.
If the Minimal Usable Subset exceeds the time allocated, the project should be re-evaluated.

## PRL
ID | Requirement Description | Priority | Effort (days) | Scheduled Version | Status | Comments
1 | Implement core SAMBUCA routines in Python | Must |  |  | Development | I have described this feature as "implement" rather than port, as the work will likely require some redesign of data structures and routines to achieve a more loosely-coupled system. Additional complications will be the move away from IDL/ENVI-specific file formats
2 | Identify essential SAMBUCA routines | Must |  |  | Complete
7 | Establish version control repository on Stash | Must |  |  | Complete
8 | Identify any blocks to using Python 3 | Must |  |  | Complete | Python 3 is preferable, but there may be blocks to this, such as an AGDC requirement for Python 2
5 | Parallel execution in Python | Must |  |  | New | Should not be dependent on Workspace or AGDC.
4 | AGDC integration | Must |  |  | New | It is anticipated that this feature will be implemented with support from GA developers. Development will probably overlap both planned eRCPs.
6 | Parallel execution on NCI | Must |  |  | New
11 | Implement data ingestion routines in Python | Must |  |  | New | Does not include the GUI component. Hard-coded paths will be sufficient to test.
15 | PySambuca must be able to operate as a standalone Python application. Use of AGDC and GUI must be optional. | Must |  |  | Complete | This means that careful thought must be given to interactions of the per-pixel processing in PySambuca and the AGDC. Is there a way to write the Python routines in such a way that they can be used in both contexts? A second ramification is that the parallel execution framework must be independent of both AGDC and Workspace (both have in-built parallel execution). IPython is an attractive option. It is open source and a proven approach to parallel execution from Python.
3 | Design / identify requirements for new GUI | Should |  |  | New | The new GUI will be implemented in a second eResearch Collaboration Project. Identifying the GUI requirements will be valuable prior to that project
12 | Provide guidance on paths to Open Source | Should |  |  | New | Licensing, collaboration, amount of control required over code, code citations & DOI, DAP etc
10 | Evaluate options for new GUI (Workspace, or native Python GUI) | Could |  |  | Complete | Not a "must" requirement until the second eRCP
13 | Investigate HDF as a data container for outputs | Could |  |  | New
9 | Temporarily graft the existing IDL GUI to the new Python core | Won't |  |  | Won't implement | Not required. Using Python scripts as drivers for the new core will be sufficient during initial development
14 | Implement new Python-compatible GUI | Won't |  |  | New | Central focus of second work phase
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## Lookups
Moscow | Status
Must | Analysis
Should | Complete
Could | Development
Won't | New
TBD | Won't implement